|  |  |  |
| --- | --- | --- |
| **Month** | **Activity/Intervention** |  |
| **Oct 2023** | **Recruitment of Organisations**  | Recruitment was targeted to BAME groups where Covid-19 and the Flu vaccination uptake was found to be low in3 PCN areas |
| **Nov 2023**  | **Launch to gain understanding of the Health Creation Framework*** Support community leads in their understanding of health creation and how to apply framework to vaccine uptake.
* VCSE organisations attendance mandatory
 | **Launch Agenda**[**P:\Current Projects\Health Creation - Vaccination\Launch info\Agendas\Launch agenda FINAL\_21 November 2023.docx**](file:///P%3A%5CCurrent%20Projects%5CHealth%20Creation%20%20-%20Vaccination%5CLaunch%20info%5CAgendas%5CLaunch%20agenda%20FINAL_21%20November%202023.docx)**Launch Presentation**[**..\Launch info\Presentation\Workshops presentations slides v1.0\_21 November 2023 - Mrupdated.pptx**](../Launch%20info/Presentation/Workshops%20presentations%20slides%20v1.0_21%20November%202023%20%20-%20%20Mrupdated.pptx) |
| **Nov 2023- March 2023** | **Project Planning and implementation*** 1-1 project management support session with VCSE leads to plan projects
* Support provided throughout project to address concerns and barriers to project implementation
 | **Project Case Studies x 3**(to be updated) |
| **Jan 2024** | **What does it mean to be a ‘Health Creator’ session** * VCSE organisation workshop led by project manager.
 | **Session Agenda**[**P:\Current Projects\Health Creation - Vaccination\What is a Health Creator Session\HC session.docx**](file:///P%3A%5CCurrent%20Projects%5CHealth%20Creation%20%20-%20Vaccination%5CWhat%20is%20a%20Health%20Creator%20Session%5CHC%20session.docx)**Session Presentation**[**..\What is a Health Creator Session\Workshops presentations slides.pptx**](../What%20is%20a%20Health%20Creator%20Session/Workshops%20presentations%20slides.pptx)**Session report (from VCSE lead and Health Creators)**[**..\Reports\Guidance Hub\Guidance Hub- what is a health creator session report.pdf**](../Reports/Guidance%20Hub/Guidance%20Hub-%20what%20is%20a%20health%20creator%20session%20report.pdf) |
| **Jan-Jun 2024** | **Support to build a health creating network.**Monthly on-line 1.5-hour workshop attended by all health creating team  | Purpose: To share best practice, reflection on work, trouble shooting and plan further activity  |
| **Feb 2024** | **Community Health Creators established.**The volunteers trained to be Health Creators via the ‘What is a Health Creator’ session supporting their communities/groups as part of the project  |  |
| **Feb 2024** | **Community Health Creator Platform Roll Out*** Members website managed by project manager
* Content input by all VCSE leads and health creators
 | Purpose: Enabling information sharing and celebration amongst members utilising off the shelf volunteer management platforms |
| **Mar 2024** | **Review**Feedback from organisations of activity/intervention impact  | (to be updated) |
| **Jul 2024** | **Celebration Ceremony** | **Celebration Brief** |
| **Sep 2024** | **Report**  | (to be completed) |